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Introduction

This quality plan provides instructions for the revision process of SSR-6 (Rev. 1) that will incorporate the proposals for change that have been accepted by TRANSSC according to the 2021 Transport Regulation Review Quality Plan.

The process of revising SSR-6 (Rev. 1) will follow the 14 Step process for revising IAEA Safety Standards Series publications as laid out in SPESS B, Manual for the review process for draft Nuclear Security Series Publications and for the application of SPESS A for the IAEA Safety Standards. Details of the application of the SPESS process to the revision of SSR-6 (Rev. 1) and a proposed timeline for the completion of the steps are included in this Quality Plan. SPESS B should also be consulted regarding details of the completion of the 14 steps. In general, the numbering of the steps in this Quality Plan corresponds to the step numbers in SPESS. However, certain additional activities that are unique to the revision of SSR-6 (Rev. 1) are included and are numbered with the step number and an asterisk, i.e. STEP 12* on tacit approval of the final edited text by TRANSSC and STEP 13* on the submission of proposed changes to SSR-6 (Rev. 1) to UNECE for inclusion in the UN Orange Book. 



[bookmark: _Toc127256419]Schedule Overview
The following schedule includes the planned times for major activities.

	Activity
	Start 
	End

	STEP 1: Preparation of DPP
	July 2022 
	18 August 2022

	
STEP 2: Internal review of the DPP (Approval by the Coordination Committee)
	11 August 2022
	18 August 2022

	
STEP 3: Review of the DPP by the Review Committees 
	26 August 2022
	2 December 2022

	
STEP 4: Review of the DPP by the CSS (approval by CSS)
	23 March 2023
	23 May 2023

	
STEP 5: Development of revised manuscript of SSR-6 (Rev. 2)Preparing the draft publication (including activities at TRANSSC 46)
	December 2022
	July 2023

	
STEP 5*: Development of modified text for proposals that were designated as “Accepted, but modified” during the Review Cycle/TRANSSC 45
	December 2022
	20 April 2023

	
STEP 5**: Review of revised text at TRANSSC 46 (NB: Authors of proposals may coordinate with the TTEGs for review of the revised text in advance of TRANSSC 46)
	5 June 2023
	9 June 2023

	
STEP 6: First internal review of SSR-6 (Rev. 2) (Approval by the Coordination Committee
	1 August 2023
	31 August 2023

	
STEP 7: First review of the draft publication by the Review Committees (Approval for submission to Member States for comments)
	31 August 2023
	December 2023

	
STEP 8: Soliciting comments by Member States
	December 2023
	April 2024

	
[bookmark: _Hlk119653369]STEP 9: Addressing comments by Member States (including activities at TRANSSC 48)
	April 2024
	July 2024

	
STEP 10: Second internal review of the draft publication (Approval by the Coordination Committee)
	August 2024
	August 2024

	
STEP 11: Second review of the draft publication by the review Committee(s) (Approval of the draft)
	September 2024
	November 2024

	
	
	

	STEP 12: Editing of the draft publication in MTCD and endorsement of the draft publication by the CSS, establishment by the Publications Committee and editing
	December 2024
	April 2025

	
STEP 12*: Tacit approval of the final edited text by TRANSSC
	May 2025
	May 2025

	
[bookmark: _Hlk119676591]STEP 13: Approval by the Board of Governors
	June 2025
	September 2025

	
STEP 13*: Submittal of SSR-6 (Rev. 2) to UNECE
	October 2025
	March 2026

	
	
	

	STEP 14: Publication
	October 2025
	January 2026
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STEP 1: Preparation of Document Preparation Profile (DPP)

Who is involved in this activity:
Secretariat

What is the purpose of this activity:
· Ensure that resources for the revision are properly reflected in the IAEA’s Programme and Budget
· Ensure that the DPP should is prepared in accordance with the criteria described in SPESS A Section 2.B
· Ensure that all organizational units of the Department of Nuclear Safety and Security (and where appropriate other Departments) are offered an opportunity to collaborate on the draft DPP
How will this be achieved:
TSU[footnoteRef:2] drafts the DPP in collaboration/coordination with other organizational units of the Agency. [2:  TSU is the Agency’s Transport Safety Unit.] 


When should this take place:
July 2022 to 18 August 2022 [NB: The DPP is prepared in advance of the decision to revise SSR-6 (Rev. 1) to save time during a prospective Revision Cycle.]

Input required for this activity:
Information about proposals received during the Review Cycle. 

Output from this activity:
Draft DPP

Resources:
Secretariat/TSU resources for drafting the DPP

NOTES

[bookmark: _Toc127256421]
STEP 2: Internal review of the DPP (Approval by the Coordination Committee)

Who is involved in this activity: 
Secretariat

What is the purpose of this activity:
· Verification of compliance of the DPP with the principles of SPESS
· Verification that intra-departmental collaboration has been offered
· Review of the robustness of the proposal, the quality of the justification, and its compliance with the criteria in terms of the structure of the Safety Standards Series
· Verification that the appropriate Review Committees[footnoteRef:3] have been identified [3:  The Review Committees for the revision of SSR-6 (Rev. 1) are TRANSSC, RASSC, WASSC, NUSSC, EPReSC and NSGC.] 

· Resolve any outstanding comments on the DPP
How will this be achieved:
Submittal of DPP to Coordination Committee[footnoteRef:4]. Review and resolution of comments received from organizational units within the Agency, including NSOC/SSDS[footnoteRef:5].  [4:  The Coordination Committee is an internal Agency committee with the objective of ensuring coherency, consistency and quality of the IAEA Safety Standards Series and the IAEA Nuclear Security Series and to facilitate the coordination for other publications of the Department of Nuclear Safety and Security.]  [5:  SSDS is the Safety Standards and Security Guidance Development Section within the Department of Nuclear Safety and Security. ] 


When should this take place:
11 – 18 August 2022 

Input required for this activity:
Draft DPP prepared by TSU. 

Output from this activity:
Draft DPP that is approved by the Coordination Committee. 

Resources:
Secretariat time to produce and review draft DPP.

 

[bookmark: OLE_LINK2]

[bookmark: _Toc127256422]STEP 3: Review of the DPP by the Review Committees

Who is involved in this activity:
Secretariat, members of TRANSSC, RASSC, WASSC, NUSSC, EPReSC, NSGC

What is the purpose of this activity:
Validation, from a Member State point of view, of need; validation of the scope and the place in the structure, in accordance with the scope of the Review Committees Committee. 

How will this be achieved:
[bookmark: _Hlk119489620]Draft DPP is posted for review by the Review Committees. Comments are provided by members of the Review Committees and appropriate changes made to the DPP. A revised DPP is posted in advance of the meetings of the Review Committees and discussed during their meetings. 

When should this take place:
From 26 August 2022 to 2 December 2022, i.e. from two months before the meeting of the first Review Committee until the end of the meeting of the last Review Committee, i.e. TRANSSC.

Input required for this activity:
Draft DPP from STEP 2.

Output from this activity:
Revised DPP that has been approved by the Review Committees.

Resources:
[bookmark: _Hlk119490080]Secretariat resources to revise DPP and make presentations. Member States’ resources to review the DPP and provide comments.


[bookmark: _Toc127256423][bookmark: _Hlk100671236][bookmark: OLE_LINK3]
STEP 4: Review of the DPP by the CSS (approval by CSS)

Who is involved in this activity:
Secretariat, CSS

What is the purpose of this activity:
Approval of the DPP with validation of need by Member States, prioritization, scope, identification of Committees to be involved in the review process.

How will this be achieved:
Draft DPP is posted for review by the CSS. Comments are provided by members of the CSS and appropriate changes made to the DPP. A revised DPP is posted in advance of the meeting of the CSS and discussed during their meeting. 

When should this take place:
The draft DPP should be posted two months prior to CSS’s meeting which will start on 23 May 2023, i.e. by 23 March 2023. The DPP will be presented and discussed at the CSS meeting in April 2023. 

Input required for this activity:
Draft DPP approved by the Review Committees.

Output from this activity:
Final DPP 

Resources:
Secretariat resources to revise DPP and make presentations. Member States’ resources to review the DPP and provide comments.


[bookmark: _Toc127256424]
STEP 5: Development of revised manuscript of SSR-6 (Rev. 2)Preparing the draft publication

Who is involved in this activity:
[bookmark: _Hlk119653428]Secretariat, members and observers of TRANSSC, TRANSSC Technical Expert Groups (TTEG), consultants

What is the purpose of this activity:
Develop the first draft of SSR-6 (Rev. 2) that incorporatesbased on the ‘accepted’ and ‘accepted, but modified’ proposals from the Review Cycle/TRANSSC 45.

How will this be achieved:
The Secretariat will facilitate the development of a manuscript of the first draft of SSR-6 (Rev. 2) in collaboration and consultation with consultants, members and observers of TRANSSC, and members of TTEGs. It is planned that some of these activities will take place at TRANSSC 46. Also, at TRANSSC 46, information about the development of the revised draft will be presented and feedback solicited as part of the consensus building process for proposed changes. The output of STEP 5* and STEP 5** will provide input to the development of the file.

When should this take place:
[bookmark: _Hlk100046565]December 2022 to July 2023; consultancy meeting to develop draft SSR-6 (Rev. 2) on 16 – 20 January 2023; consultancy meeting to incorporate modified text from proposals designated as ‘accepted, but modified’ on 2 – 5 May 2023; draft SSR-6 (Rev. 2) posted for TRANSSC on 5 May 2023; TRANSSC 46 is scheduled for 5 – 9 June 2023; revisions to the draft may take place after TRANSSC 46.

Input required for this activity:
‘Accepted’ and modified text for ‘accepted, but modified’ proposals from the Review Cycle. 

Output from this activity:
First draft of SSR-6 (Rev. 2). 

Resources:
[bookmark: _Hlk119576559]Secretariat time and effort to facilitate/organize this effort. Participation of consultants, members and observers of TRANSSC, and members of TTEGs.


[bookmark: _Toc127256425]STEP 5*: Development of modified text for proposals that were designated as “Accepted, but modified” during the Review Cycle/TRANSSC 45

Who is involved in this activity:
Authors of proposals, stakeholders

What is the purpose of this activity:
Develop modified text for proposals that were designated as ‘accepted, but modified’ during the Review Cycle/TRANSSC 45.

How will this be achieved:
Authors of proposals that were designated as ‘accepted, but modified’ will develop modified text that takes account of the recommendations of the TTEGs and TRANSSC. Stakeholders should be consulted during this process. Modified text will be sent by the authors to the Secretariat and will be entered into the draft SSR-6 (Rev. 2) and the four TTEG files/resolution tables.

When should this take place:
Modified text may be developed starting from the end of TRANSSC 45, i.e. 2 December 2022. Modified text should be submitted by the author of the proposal to the Secretariat by 20 April 2023.

Input required for this activity:
Proposals designated as ‘accepted, but modified’ during the Review Cycle/TRANSSC 45. 

Output from this activity:
Modified text for ‘accepted, but modified’ proposals. 

Resources:
Time and effort of authors to revise text and to consult with stakeholders.




[bookmark: _Toc127256426]STEP 5**: Review of revised text at TRANSSC 46 (NB: Authors of proposals may coordinate with the TTEGs for review of the revised text in advance of TRANSSC 46)

Who is involved in this activity:
Secretariat, members and observers of TRANSSC, TRANSSC Technical Expert Groups (TTEG)

What is the purpose of this activity:
· To perform a quality control check on the draft SSR-6 (Rev. 2); specifically, to ensure that text for all ‘accepted’ and ‘accepted, but modified’ proposals has been entered appropriately in the manuscript of a draft SSR-6 (Rev. 2)
· To improve the quality of the revised text
· To build consensus for the changes in the draft SSR-6 (Rev. 2)
How will this be achieved:
· The TTEGs will review all revised text in the draft SSR-6 (Rev. 2) for the proposals for which they were assigned primary responsibility. The TTEGs should assess whether the revised text is acceptable and develop suggestions for improvement. Initial discussions on possible transitional arrangements related to the revised text should be held. The TTEG meetings will be held in a face-to-face format at TRANSSC 46, but may also take place virtually or otherwise in advance of TRANSSC 46. The TTEG chairs will report the results of their discussions to TRANSSC in plenary.
· During plenary, the opinions of the members of TRANSSC will be solicited regarding the proposed changes to the text; suggestions for improvement will be solicited; also, the members of TRANSSC will be asked whether there are proposed changes that a member ‘cannot live with’. For such proposals/text, discussions will be held about possible ways in which a consensus could be achieved.
· According to the outcome of the discussions, changes to the revised text will be made in the draft SSR-6 (Rev. 2).
When should this take place:
TRANSSC 46 is scheduled for 5 – 9 June 2023. TTEGs may review revised text in advance of TRANSSC 46.

Input required for this activity:
First draft of SSR-6 (Rev. 2) in which revised text has been entered for ‘Accepted’ and ‘accepted, but modified’ proposals from the Review Cycle. 

Output from this activity:
First draft of SSR-6 (Rev. 2) for which a quality control check has been performed, improvements to revised text have been made and consensus has been built. 

Resources:
Secretariat time and effort to organize this effort. Participation of members and observers of TRANSSC, and members of TTEGs.

[bookmark: _Toc127256427]
STEP 6: First internal review of SSR-6 (Rev. 2) (Approval by the Coordination Committee)

Who is involved in this activity:
The Secretariat

What is the purpose of this activity:
Verification of the quality of the draft, compliance with the approved DPP, coherency, consistency, and validation of coordination among organizational units of the Agency.

How will this be achieved:

Submittal of first draft of SSR-6 (Rev. 2) to the Coordination Committee. Review and resolution of comments received from organizational units within the Agency, including review of the draft by NSOC/SSDS. In particular, the draft is reviewed for its consistency with other publications and compliance with the DPP. 

When should this take place:
Following the preparation of the draft publication in STEP 5 until the meeting of the Coordination Committee on 31 August 2023. The draft document should be posted for review by the Coordination Committee no later than 17 August 2023. Approval by the Coordination Committee must take place no later than 31 August 2023, which is two months before the meeting of the first Review Committee (WASSC), which is scheduled for the week of 30 October 2023.

Input required for this activity:
Draft publication from STEP 5.

Output from this activity:
Draft of SSR-6 (Rev. 2), which has undergone technical review by NSOC/SSDS and internal review.   

[bookmark: _Hlk100045314]Resources:
Secretariat time to review the draft document, to provide comments and to resolve them. 
 
[bookmark: _Toc127256428]
STEP 7: First review of the draft publication by the Review Committee(s) (Approval for submission to Member States for comments)

Who is involved in this activity:
The Secretariat, TRANSSC, and other Review Committees

What is the purpose of this activity:
To ensure the quality and accuracy of draft, receive approval for Member State consultation, and verify consistency with the DPP.

How will this be achieved:
[bookmark: _Hlk119653553]Draft document is posted for review by the Review Committees. Members of Review Committees review the proposed changes and post comments. Secretariat resolves comments which may involve collaboration and consultation with consultants, members and observers of TRANSSC, and members of TTEGs. Presentations made by the Secretariat to the Review Committees about the comments received and their resolution. Discussions and the achievement of consensus during the meetings of Review Committees. 

When should this take place:
[bookmark: _Hlk119662506]The draft document should be posted by the Secretariat no later than 31 August 2023, which is two months before the first Review Committee (WASSC) meets. Comments by Review Committees should be posted no later than 9 October 2023, i.e. three weeks before the scheduled meeting of WASSC. Secretariat resolves comments and posts resolution table and revised draft by 23 October 2023, i.e. one week before the meeting of WASSC. Presentations on the comments submitted and their proposed resolution will take place at the fall meetings of the Review Committees. 

Input required for this activity:
Draft publication that is the output of STEP 6.

Output from this activity:
[bookmark: _Hlk119654508]Resolution table and revised draft that reflects the resolution of the comments.

Resources:
[bookmark: _Hlk119654527]Secretariat time and effort to develop resolution table and revised draft. Participation of consultants, members and observers of TRANSSC, and members of TTEGs.


[bookmark: _Hlk100671546][bookmark: _Toc127256429]
STEP 8: Soliciting comments by Member States

[bookmark: _Hlk109652956]Who is involved in this activity:
Secretariat and Member States.

What is the purpose of this activity:
International consensus building

How will this be achieved:
Comments by all Member States on the revised draft of SSR-6 (Rev. 1) will be solicited during a 120-day comment period through the issuance of a Note Verbale by the Secretariat. 

When should this take place:
Following approval of the draft of SSR-6 (Rev. 2) by the Review Committees. The comment period will be from December 2023 to April 2024.

Input required for this activity:
Draft of SSR-6 (Rev. 2) that has been approved by the Review Committees. 

Output from this activity:
Comments from Member States on proposed changes to SSR-6 (Rev. 1).

Resources:
The Secretariat will issue a Note Verbale and collate the comments that are received. Member States will provide comments to the Secretariat. 



[bookmark: _Hlk100669521]
[bookmark: _Toc127256430][bookmark: _Hlk109652621]
STEP 9: Addressing comments by Member States

Who is involved in this activity:
Secretariat, members and observers of TRANSSC, TRANSSC Technical Expert Groups (TTEG), consultants

What is the purpose of this activity:
Incorporation of comments into the draft SSR-6 (Rev. 2) reflecting international consensus 

How will this be achieved:
Secretariat resolves comments which may involve collaboration and consultation with consultants, members and observers of TRANSSC, and members of TTEGs. A resolution table of the comments and a revised draft of SSR-6 (Rev. 2) that reflects these comments will be prepared. It is expected that some of these activities will take place at TRANSSC 48. Also, at TRANSSC 48, information about the development of the revised draft will be presented and feedback solicited as part of the consensus building process for proposed changes. 

When should this take place:
From the end of the 120-day comment period (April 2024) until July 2024; TRANSSC 48 is expected to be held in June 2024.

Input required for this activity:
Member States comments from STEP 8.

Output from this activity:
Resolution table and revised draft that reflects the resolution of the comments.

Resources:
Secretariat time and effort to develop resolution table and revised draft. Participation of consultants, members and observers of TRANSSC, and members of TTEGs.


[bookmark: _Toc127256431]STEP 10: Second internal review of the draft publication (Approval by the Coordination Committee)

Who is involved in this activity:
The Secretariat.

What is the purpose of this activity:
To ensure the quality of the draft and internal consistency

How will this be achieved:
Submittal of draft of SSR-6 (Rev. 2) and resolution table from STEP 9 to Coordination Committee and NSOC-SSDS. Review and resolution of comments received from organizational units within the Agency, including the results of comprehensive textual review of the draft by NSOC/SSDS. Approval of revised draft and resolution table by Coordination Committee. 

When should this take place:
It is necessary that the activities of STEP 10 be completed in August 2024 so that the revised draft and resolution table can be posted two months in advance of the meetings of the Review Committees in fall 2024. 

Input required for this activity:
The input is the revised draft of SSR-6 (Rev. 2) and resolution table that are the output of STEP 9.

Output from this activity:
[bookmark: _Hlk119663292]Resolution table and revised draft of SSR-6 (Rev. 2), which has undergone comprehensive textual review by NSOC/SSDS and internal review.

Resources:
Secretariat time to review the draft document, to provide comments and to resolve them.  


[bookmark: _Toc127256432][bookmark: _Hlk109652912]STEP 11: Second review of the draft publication by the review Committee(s) (Approval of the draft)

Who is involved in this activity:
The Secretariat, TRANSSC, and the other Review Committees

What is the purpose of this activity:
Validation of the consideration of Member States’ comments; conformance with requirements of the Safety Standards Series, the IAEA Safety and Security Glossary 2022 (Interim) Edition, and the Agency’s mandate and policies; final approval

How will this be achieved:
Draft document and resolution table is posted for review by the Review Committees. Members of Review Committees review the proposed changes and make comments. Secretariat resolves any outstanding comments which may involve collaboration and consultation with consultants, members and observers of TRANSSC, and members of TTEGs. Presentations made by the Secretariat to the Review Committees about the comments received and their resolution. Discussions during the meetings of Review Committees. 

When should this take place:
[bookmark: _Hlk119675655]The draft document should be posted by the Secretariat no later than the end of August 2024, i.e. at least two months before the meeting of the first Review Committee. Comments by Review Committees should be posted no later than three weeks before the meeting of the first Review Committee, i.e. approximately 7 - 15 October 2024. Secretariat resolves comments and posts resolution table and revised draft by late October 2024, i.e. one week before the meeting of the first Review Committee. Presentations on the comments submitted and their proposed resolution will take place at the fall 2024 meetings of the Review Committees. 

Input required for this activity:
The output from STEP 10, i.e. a resolution table and a revised draft of SSR-6 (Rev. 2), which has undergone comprehensive textual review by NSOC/SSDS and internal review.

Output from this activity:
Approved draft for editing and final endorsement.

Resources:
[bookmark: _Hlk119676033]Secretariat time and effort to develop resolution table and revised draft. Participation of consultants, members and observers of TRANSSC, and members of TTEGs.



[bookmark: _Toc127256433][bookmark: OLE_LINK4]
STEP 12: Editing of the draft publication in MTCD and endorsement of the draft publication by the CSS, establishment by the Publications Committee and editing 

Who is involved in this activity:
Secretariat, CSS

What is the purpose of this activity:
Editing of the draft for clarity of language and Agency style and endorsement of the Committees’ decision to approve the draft to the BoG. 

How will this be achieved:
Submission of SSR-6 (Rev. 2) to Publications Committee for approval for editing. Resolution of any issues raised.
Draft document is posted for review by CSS. Members of CSS review the draft. Secretariat resolves any CSS comments. Presentation made by the Secretariat to CSS about proposed changes and the resolution of comments received from CSS. Discussion during the meeting of CSS. The CSS endorses the final draft.

When should this take place:
Submission of the draft publication to the Publications Committee should take place as soon as possible after it is approved by the Review Committees, i.e. by approximately December 2024.

The draft document should be posted by the Secretariat at least two months before the CSS meeting in April 2025, i.e. by approximately February 2025. Comments by CSS should be posted no later than three weeks before its meeting. Secretariat resolves comments and posts a resolution table and revised draft by one week before the CSS meeting April 2025. Presentations on the comments submitted and their proposed resolution will take place at the April 2025 meeting of CSS. 

Input required for this activity:
Draft of SSR-6 (Rev. 2) that has been approved by the Review Committees. 

Output from this activity:
Draft of SSR-6 (Rev. 2) that has been approved by CSS and edited for publication according to Agency style. 

Resources:
Secretariat resources to develop resolution table and revised draft. 
CSS time to read and comment.


[bookmark: _Toc127256434]STEP 12*: Tacit approval of the final edited text by TRANSSC 

Who is involved in this activity:
Secretariat, TRANSSC

What is the purpose of this activity:
To ensure that a consensus is achieved on the final edited text of SSR-6 (Rev. 2).

How will this be achieved:
TRANSSC will be consulted through the application of a tacit approval procedure whereby the final edited text of SSR-6 (Rev. 2) is distributed by the Secretariat to TRANSSC members for a comment period of two weeks. 

NB: If, as a result of this tacit approval procedure, TRANSSC agrees changes to the text of SSR-6 (Rev. 2) that were not endorsed by CSS, CSS will be consulted regarding these new changes through a tacit approval procedure.

When should this take place:
As soon as the final edited text is available from MTCD[footnoteRef:6]. [6:  MTCD is the Agency’s publishing section.] 


Input required for this activity:
Final edited version of SSR-6 (Rev. 2). 

Output from this activity:
Final edited text of SSR-6 (Rev. 2) that has been approved by TRANSSC. 

Resources:
Secretariat resources facilitate the tacit approval procedure and TRANSSC efforts to review and comment on the revised text.



[bookmark: _Toc127256435]STEP 13: Approval by the Board of Governors 

Who is involved in this activity:
Secretariat, Board of Governors

What is the purpose of this activity:
Approval at the highest level of a safety standard publication

How will this be achieved:
Section Head, Programme and Strategy Coordination Section, NSOC, initiates SEC/PMO clearance process. Standards specialist submits draft publication for translation by Language Services. Board of Governors reviews draft SSR-6 (Rev. 2) for establishment as a safety standard. 


When should this take place:
SEC/PMO clearance process: As soon as possible after STEP 12A, allowing 5 weeks for completion of clearance process, i.e. June 2025.
Draft publication translation into official languages: As soon as possible after Step 12, allowing two months for translation, i.e. June 2025. 
Board of Governors meeting in September 2025.

Input required for this activity:
Draft of SSR-6 (Rev. 2) that has been approved by CSS. 

Output from this activity:
Draft of SSR-6 (Rev. 2) that has been approved by the Board of Governors.

Resources:
Secretariat resources related to submittal of the publication for consideration by the Board of Governors and translation of the draft publication. Board of Governors time to read and comment.  
[bookmark: _Hlk119676567]

[bookmark: _Toc127256436][bookmark: _Hlk119739294]STEP 13*: Submittal of SSR-6 (Rev. 2) to UNECE 

Who is involved in this activity:
Secretariat

What is the purpose of this activity:
To have the changes to the text in SSR-6 (Rev. 2) incorporated into the UN Orange Book.

How will this be achieved:
Secretariat submits changes to SSR-6 (Rev. 2) to the UNECE for consideration by the Sub-Committee of Experts on the Transport of Dangerous Goods. A table with a column showing deleted text and a column showing additional text will be provided by the Secretariat. 

When should this take place:
As soon as the Board of Governors approves the revised SSR-6 (Rev. 2), i.e. in October 2025, but no later than March 2026.

Input required for this activity:
Draft of SSR-6 (Rev. 2) that has been approved by the Board of Governors. 

Output from this activity:
Documents submitted to UNECE: track changes version of SSR-6 (Rev. 2); A table with a column showing deleted text and a column showing additional text. 

Resources:
Secretariat resources to prepare documents to be submitted to the UNECE.  


[bookmark: _Toc127256437]STEP 14: Publication

Who is involved in this activity:
Secretariat

What is the purpose of this activity:
Publication on web site and in print

How will this be achieved:
MTCD editor prepares final proof layout and finalizes the production process. Standards Specialist and technical officer review final proofs. Publication to the web and printing of hard copies.

When should this take place:
Final preparation of the publication should begin as soon as SSR-6 (Rev. 2) is approved by the Board of Governors, i.e. by October 2025.

Input required for this activity:
Draft of SSR-6 (Rev. 2) that has been approved by the Board of Governors. 

Output from this activity:
Electronic and hard copies of published versions of SSR-6 (Rev. 2).

Resources:
Secretariat resources to prepare and review final proof layout and finalize the production process.  


